## Example
Inspection & Test Plan
| ITP Title: |  |  |  | ITP Input Information |  |  |  |  | Name | Role |  | Date | Signature
| ITP Ref: |  |  |  | Source / Document | Reference | Revision |  | ITP Produced by:
| ITP Rev: |  |  |  | Lessons learned
[5 empty] | Drawings |  |  |  | ITP Produced by:
| ITP Scope Description |  |  |  | Specifications
| This ITP relates to the following works: 1) 2) It should be noted that this ITP does not cover the following aspects: a) |  |  |  | Manufacturer's requirements |  |  |  | ITP Reviewed by:
Contract requirements
[5 empty] | Project Management Plan |  |  |  | ITP Reviewed by:
Design Management Plan
ITP Authorised for use by:
Abbreviations
| PC: Principal Contractor; BCO: Building Control Officer; S / C: Subcontractor; QMP: Quality Management Plan; WQF: Works Quality File |  |  |  | Inspection / Test Key | SFA: Submit for Approval | H: Hold Point | AU: Audit | I (100): Inspection 100% | S (100): Surveillance 100% |  | W (100): Witness 100%
[6 empty] | SFI: Submit for Information | A: Archive | n / a: Not Applicable | I (10): Inspection 10% | S (10): Surveillance 10%) |  | W (10): Witness 10%
[6 empty] | DC: Daily Check | WC: Weekly check
STAGE | Ref. | What is the activity or quality input? | Requirement |  | What will be done to ensure compliance | How will compliance be demonstrated? | Evidence |  | Who has responsibility for closing out this requirement? | What resources are required? | Inspection / Test Details & Parties Involved
|  |  | Where from? | What is the requirement? |  |  | Description | Location |  |  | S / C | PC | PC Client | Other 1 | Other 2
BCO
Pre Construction | 1.1 | Risk Assessment & Method Statement | Project Management Plan; Section: | The S / C RAMS must be accepted by the PC prior to works commencing. | Bespoke RAMS will be produced 'fit for purpose' for the works which also meet the legal & PC requirements; RAMS to be submitted to PC min. 4 weeks prior to start. | The PC will provide confirmation that the RAMS is 'A' or 'B' status via signed RAMS Review Record Form. | Written confirmation from PC confirming RAMS is 'A' or 'B' status via RAM Review Record Form. | Completed RAMS Review Record form to be filed in Section 2 of WQF. | S / C Project Manager | Input from H & S Adviser; Project Manager to dedicate appropriate time to production of RAMS | H | H | n / a | n / a
| 1.2 | Design approval | Design Management Plan: Section: | The design must be AFC status prior to start. | PC to issue AFC drawings; S / C Supervisor to check drawings when received to verify AFC Status. | S / C Supervisor to print drawings when received, date stamp and file in Design Information Master Folder held in the S / C Site Office. | Design documentation held in the Design Information Master Folder will be AFC status. | Hard copy design information held in the Design Information Master Folder; Electronic versions of information are held on the design portal system. | PC to ensure design is AFC; S / C Project Manager to liaise with PC; S / C Supervisor to ensure Design Information Master Folder is held in the S / C Site Office. | Project Manager to dedicate appropriate time for design input; S / C Supervisor to undertake daily check of information held on design portal system. | H | H | n / a | n / a
| 1.3 | Competence | S / C QMP | All persons must be competent to undertake their role. | S / C Director to appoint Project Manager; Competence review of supervisors; Supervisors to review operative workmanship; Training matrix to be populated; Toolbox talks to be completed regularly. | S / C to appoint Project Manager in writing; Supervisors to appoint 'black hat' supervisors using Supervisor Competence Form; Supervisors to undertake surveillance of operatives; Supervisors to complete regular toolbox talks; Training Matrix to be displayed; Training records to be maintained. | Director's letter; Supervisor Competence Form; Surveillance Form; Signed toolbox talk briefing sheets; Formal training records to maintained. | Evidence to be included in Section 4 of WQF; Toolbox talk records to be included in Section 5 of WQF | Director to appoint S / C Project Manager; Project Manager to oversee competence of site personnel: S / C Supervisors to check competence of operatives. | Director, Project Manager and Supervisors to allocate applicable time. | H | H | n / a | n / a
| 1.4 | Latest design information issued
| 1.5 | Strategy to protect works
| 1.6 | Site quality briefing
| 1.7 | Auidt of factory processes (prior to commencement of off site manufacture)
| 1.8 | Equipment calibration
| 1.9 | Mock-up to be produced
| 1.1 | Samples
Material Conformity | 2.1 | UKAS Accreditation
| 2.2. | Approval of Permanent Materials
| 2.3 | Material certification
| 2.4 | Material storage
Off Site Manufacture | 3.1 | Audit of off site manufacture in progress.
| 3.2 | Off site manufacture records
Site Construction | 4.1 | Pre condition survey
| 4.2 | Benchmark Standard approved
Testing & Commissioning | 5.1
Post Construction | 6.1 | Final Inspection
| 6.2 | Protection of works
| 6.3 | As-Built Information / Red-Line Drawings
| 6.4 | Operating & Maintenance Manual Information
| 6.5 | Client Handover
| Subcontractor: Confirmation of ITP Completion | [7 empty] | Principal Contractor
| We confirm that to the best of our knowledge and with respect to the stated scope of works all activities have been completed in accordance with the relevant requirements. We have maintained an adequate 'weight of evidence' to demonstrate compliance which has been made available to relevant parties. | [7 empty] | We confirm that with respect to the stated scope of works and to the best of our knowledge works been completed in accordance with all relevant requirements. An adequate 'weight of evidence' has been maintained to demonstrate compliance and made available to relevant parties.
| Name |  | Role |  | Date | Signature |  |  | Name | Role | Date |  | Signature

## Proforma
Inspection & Test Plan
| ITP Title: |  |  |  | ITP Input Information |  |  |  |  | Name | Role |  | Date | Signature
| ITP Ref: |  |  |  | Source / Document | Reference | Revision |  | ITP Produced by:
| ITP Rev: |  |  |  | Lessons learned
[5 empty] | Drawings |  |  |  | ITP Produced by:
| ITP Scope Description |  |  |  | Specifications
| This ITP relates to the following works: 1) 2) It should be noted that this ITP does not cover the following aspects: a) |  |  |  | Manufacturer's requirements |  |  |  | ITP Reviewed by:
Contract requirements
[5 empty] | Project Management Plan |  |  |  | ITP Reviewed by:
Design Management Plan
ITP Authorised for use by:
Abbreviations
| PC: Principal Contractor; BCO: Building Control Officer; S / C: Subcontractor; QMP: Quality Management Plan; WQF: Works Quality File |  |  |  | Inspection / Test Key | SFA: Submit for Approval | H: Hold Point | AU: Audit | I (100): Inspection 100% | S (100): Surveillance 100% |  | W (100): Witness 100%
[6 empty] | SFI: Submit for Information | A: Archive | n / a: Not Applicable | I (10): Inspection 10% | S (10): Surveillance 10%) |  | W (10): Witness 10%
[6 empty] | DC: Daily Check | WC: Weekly check
STAGE | Ref. | What is the activity or quality input? | Requirement |  | What will be done to ensure compliance | How will compliance be demonstrated? | Evidence |  | Who has responsibility for closing out this requirement? | What resources are required? | Inspection / Test Details & Parties Involved
|  |  | Where from? | What is the requirement? |  |  | Description | Location |  |  | S / C | PC | PC Client | Other 1 | Other 2
Pre Construction
Material Conformity
Off Site Manufacture
Site Construction
Testing & Commissioning
Post Construction
| Subcontractor: Confirmation of ITP Completion | [7 empty] | Principal Contractor
| We confirm that to the best of our knowledge and with respect to the stated scope of works all activities have been completed in accordance with the relevant requirements. We have maintained an adequate 'weight of evidence' to demonstrate compliance which has been made available to relevant parties. | [7 empty] | We confirm that with respect to the stated scope of works and to the best of our knowledge works been completed in accordance with all relevant requirements. An adequate 'weight of evidence' has been maintained to demonstrate compliance and made available to relevant parties.
| Name |  | Role |  | Date | Signature |  |  | Name | Role | Date |  | Signature