## Rationale and Landscape
Concept and Developed Design - Quality Best Practice Self Assessment
Background
Typically today: 1) Construction projects have many quality metrics for the delivery phase but Clients have very few metrics for the Concept and Developed design stages of their projects. 2) Evidence from projects, supported by analysis by the GIRI (Get It Right Initiative) in the UK, shows that the average construction projects overruns its budget by 20% with worst case examples being 3-400% with time overruns of many years. The analysis concluded that many project quality issues have their root cause in the design stages of a project. Both the Client and the Architect processes often have a significant bearing on these issues. In 2020, the Chartered Quality Institute published a piece of Quality guidance called the Construction Project Lifecycle which laid out the key Quality steps required to maximise the chance of success in construction projects. This guidance sparked wide interest and positive comments around the world. These interested people felt that more guidance about Quality Best Practices in the design stages of projects would be an very useful guidance tool.
The Best Practice Tool
This Concept and Developed Design - Quality Best Practice Self Assessment tool has been developed by a small group of leading quality experts from America, Australia, Canada & the UK, from a tool developed in the Airport Infrastructure industry . The belief is that use of this tool can significantly reduce the risks faced in projects by following well proven best practices developed from around the world. This will lead to major cost avoidance, timely delivery and enhanced reputations.
When should this Tool be used?
The tool should be used during the Concept Design and Developed Design stages of a project (as defined by UK's RIBA organisation). Sometimes called Options and Scheme design stages. The starting point is the Business Case approval Gateway (or some kind of project kick off decision.) That is:- a Client/Owner has had an idea, decided that it should be explored and set aside the necessary funds to develop a more detailed proposal. At the end of the Concept stage, there may be a Recommended Option Approval Gateway, before the commencement of the Developed Design Stage. On lower risk projects, this may also include funding for the entire project. At the end of the Developed Design Stage, it is likely that the more detailed cost and schedule would be used to seek approval for the funding of the entire project. After this (and not covered by this guidance) the project would move to production design, delivery stages and then to Handover and Operation/Maintenance.
Contributors
Original work commissioned by Heathrow and lead by Helen Soulou with much input from Arup, Atkins and Jacobs. The subsequent development of the tool has been undertaken by the following with input from Ed McCann:-
Anita McReynolds Lidbury | Arcadis (USA)
David Myers | Shirley Parsons Project Services (UK)
Felipe Maya | CIH - Construction Innovation Hub (UK)
Greg Wennerstrom | Calgary Light Rail Project - Canada
Jonny Montgomery | Shirley Parsons Project Services (UK)
Martin Andrews | Martin Andrews Solutions (Australia)
Zoran Stojanovski | AECOM (Australia)

## Glossary
Glossary Concept and Developed Design - Quality Best Practice Self-Assessment
General Terminology | Generally, RIBA (Royal Institute of British Architects - UK based) terminology has been used to define the gateways and project stages between them (Concept and Developed Design), as it is broadly recognised within the construction industry. Client organisations and specific industries may use different terminologies for these purposes
Boundary diagrams | A tool for establishing what is in and out of scope for the project.
Concept Design | Concept design as defined by RIBA. Options have been considered and a single solution selected for further design work to develop detailed cost and timing estimates.
Concept Design Report | Report written by the designers at the end of the Concept Design Stage recording the recommended solution and the reasons for selection.
Developed Design | Developed design as defined by the UK based RIBA (Royal Institute of British Architects). Sufficient design detail to enable a cost estimate that satisfies the risk appetite of the client/owner.
Developed Design Report | Report written by the designers at the end of the Developed Design Stage
DMS | Document Management System
Gateway | A point in a project were the team reviews progress against plan before progressing to the next stage. Often a gateway is subject to external approval by Client/Owner management team and stakeholders. Often called Stage Gates or Milestones around the world.
Gateway Actions | Outstanding actions, agreed at the completion of the prior project stage, that must be completed in the current project stage. i.e. risks carried forward.
Handover Plan | The plan for formally handing over the finished product to the teams that will be using, operating and maintaining the facility. Includes all documentation, training, specified prove -out tests etc.
KPI | Key performance indicator
n/a | not applicable
PCM | Client/Owner Project Controls Manager - PMO member who verifies or validates project output
PMO | Client/Owner Programme (Project) Management Office. Team of people who manage the portfolio of projects.
Project Assumptions Register | Register for all assumptions made by the design team. These must be eliminated by the end of the Developed Design Stage either by design action or by being incorporated into the Risk Register
Project Complexity Assessment | An (optional) evaluation undertaken at the concept stage by Clients/Owners with large portfolios of projects. It is used to determine the complexity classification of the project and thus to establish high risk areas and the level of governance of the project. E.g. Board level approval, PMO intervention etc.
Project Management Plan | A plan provided by the Client/Owner including a description of the project, execution details project cost, schedule, risks, assumptions, resources, organization structure with roles and responsibilities, key deliverables etc. Note: Contractors may also have their own PMPs to control their part of the overall project.
Project OK to Start document | This is the document, from the client/owner, that identifies the Key Business Needs and gives formal approval for the project to start the concept evaluation phase. Applicable in ongoing framework arrangements.
QVP | Quality Verification Plan prepared by Client/Owner and the design teams using the client requirements document and designer requirements as inputs. The outputs are the required verification/validation for each requirement. i.e. drawing, modelling, ITP, commissioning and operational readiness test.
Requirements documents | The requirements may be defined in one or a number of documents. Every Requirement should have a named owner and a clear change history should be maintained within the document.
1) Highest Level - provided by the Client/Owner identifying the functional and performance requirements for the assets to be designed and constructed
2) Second Level - developed by the concept and developed designers
3) Third level - developed by the detail (production) level designers.
The highest level requirements document is a crucial part of the concept design Brief (as defined by RIBA)
Works Information | Pack of Data that forms part of the Construction contract. It defines in detail exactly what the construction team have to deliver - it can have both Client/Owner standard requirements and all specific project related data.

## Cover Sheet & SA Summary
Concept and Developed Design - Quality Best Practice Self Assessment
Business Case | [6 empty] | Project Manager
Project | [6 empty] | Quality Manager
Concept and Developed Design Director | [6 empty] | Project Office Representative
Delivery Director
Concept Design Stage
| Score |  | 0.01 | Score |  | 0.01 |  | Score | 0.01
| % of Total |  | 0.007407% | % of Total |  | 0.008333% |  | % of Total | 0.01333%
Commentary:
Developed Design Stage
| Score |  | 0.01 | Score |  | 0.01 |  | Score | 0.01
| % of Total |  | 0.006897% | % of Total |  | 0.009091% |  | % of Total | 0.01176%
Commentary:
| Scoring | Definition
| 0 | Not yet considered
| 1 | Plan in place
| 2 | Some progress
| 3 | Significant progress
| 4 | Activity complete
| 5 | Approved and documented
| n/a | Not applicable to this project |  | Note: Do not delete this table.
Plan and Mobilise Checkpoint (1)
Design Checkpoint (2)
Validate & Assure Checkpoint (3)
Plan and Mobilise Checkpoint (1)
Design Checkpoint (2)
Validate & Assure Checkpoint (3)

## Concept Evaluation Assessment
Concepts Evaluation Stage - Quality Best Practice Self Assessment | [7 empty] | Plan and Mobilise Checkpoint (1) | 0.007407%
This self assessment is designed to evaluate the confidence and maturity of a project through a specific stage of the Client Project Process, aligned with the process method guidance. The assessment is to be conducted by, at a minimum, the Project Manager together with the PMO Rep and Quality Manager. | [7 empty] | Concepts Design Checkpoint (2) | 0.008333%
[8 empty] | Validate & Assure Checkpoint (3) | 0.01333%
Business Case | 0 |  |  | Project Manager |  | 0
Project | 0 |  |  | Quality Manager |  | 0
Checkpoint Timing Guidance - Checkpoint (1) - between 5-10% of the way through the stage. Checkpoint (2) 60-70% through the stage and checkpoint (3) about 90% of the way through the stage
Plan / Schedule / Cost
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Lessons Learned from similar projects have been collected, reviewed and considered. Document conclusions in the Project Management Plan |  |  | Lessons Learned exercise for the concept evaluation stage has been completed.
Project Complexity assessment conducted (applicable to large portfolio's of projects only)
Project Management Plan in place, signed and published in DMS. Consider the value in running a peer review, if needed, include in the PMP and schedule. |  |  |  |  | Project Management Plan reviewed and updated as required.
Quality Plan for Concept and Developed Design stage in place |  |  | Quality Plan on target |  | All elements of the Quality plan complete
Prior Gateway review conducted and any actions have been resolved
Detailed schedule for Concepts Evaluation Stage in place, agreed with project team and Client/Owner and all contractor activities are integrated with external interface milestones identified. Understanding of the critical path. |  |  | Concepts Evaluation Stage schedule updated to reflect the output of the Concepts design phase.
Agree plan to develop concept level cost estimates and the required accuracy to support risk appetite of client/owner. Client/Owner should declare project cost target to meet business expectations |  |  |  |  | Validate and assure the cost plan
A high level "end-to-end" project schedule in place, aligned with the Client Project Process Guidance |  |  | High level "end-to-end" schedule updated to reflect the output of the Concepts design phase. Understanding of the critical path |  | Validate and assure the schedule
Is the brief for Delivery Contractor, or other supplier, to provide: a) buildability advice (A Constructability Review) and, b) other support (e.g. carryout surveys etc.) to next Gateway in place |  |  | Buildability advice has been sought and surveys have been completed
|  | 0 |  | 0 |  |  | 0
9 |  | 0 | 5 | 0 | 4 |  | 0
Requirements and Design Management |  |  |  | 0 |  |  | 0
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Have prior Gateway actions been resolved or plan in place (if applicable)? Have you got a fully approved "Project OK to Start" document for the project?
Have you considered: boundary diagram, concept of operations workshops, types of requirements etc. Are these activities in the schedule.
Assure that all team members and stakeholders have provided updated requirements. |  |  | Have all types of requirements been documented? Have all the relevant specs and legislation been identified? Have Safety-in-Design and Sustainability-in-Design requirements been added? |  | Requirements document has been developed further, reviewed and agreed with relevant areas of the business (e.g. Operations, Asset Owners, Maintenance, Commissioning Teams, end users and affected stakeholders)
Has the Requirements Document been updated ahead of design commencing, circulated to all team members/stakeholders and published in DMS? Are the project Client/Owner Requirements and the design requirements for the Concepts design clear, documented and referenced to the operational benefits? |  |  | Have changes to requirements that effect scope been communicated formally via the Contract mechanisms Change has been incorporated in the Basis of Design. |  | o Have any last minute changes to requirements that effect scope been communicated formally via the Contract mechanisms o Last minute change to requirements has been incorporated in the Basis of Design o Benefits quantified and linked to requirements were appropriate o Link to Benefits Plan and/or the Maintenance/ Operations Management plans where applicable..
A Design Management Plan is in place including definition of the plan for BIM and a Common Data Environment (CDE), a Design Review Schedule and a design change approval process |  |  | All design changes have been approved
The Design Brief is clear and unambiguous. Any assumptions that are needed have been specified. (See Risks and Assumptions section) |  |  | Has appropriate buildability and constructability input/advice been sought?
All the design deliverables (within the brief) are clear? |  |  |  |  | All design deliverables met
Required models and drawings to the Client/Owner specified format are clear? |  |  | All models and drawings are being prepared |  | All models and drawings have been delivered
Are the timescales for the concept design aligned with the level of risk tolerated by the owner/client? i.e. The selected option will not be perfect unless the time allowed is infinite. |  |  | Is the design work on target? i.e. Is the design work driving satisfactorily to a timely conclusion? Are the timescales and risks still aligned? Are the number of unknowns reducing?
Plan developed to load the requirements into the QVP (Quality Verification Plan), staring with the Client Requirements and benefits |  |  | QVP has been loaded with Client level requirements and is now owned by the Concept Evaluation Designer. Concepts design requirements have been added (this can be part of the Requirements document) |  | Updated QVP ready to be handed over to the Developed Design designer
Basis of design aligns with Requirements. |  |  | Determine future on-site survey scope needed to inform the developed design. Incorporate these surveys into the project schedule.
|  | 0 |  | 0 |  |  | 0
11 |  | 0 | 8 | 0 | 5 |  | 0
Risks / Assumptions |  |  |  | 0 |  |  | 0
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Risks & assumptions have been explored & captured. Project Assumptions Register is published in DMS. |  |  | Risk register with mitigation plans exist and are published in DMS. |  | Risk register with mitigation plans has been reviewed and updated in line with the Concept selected.
|  |  | Have assumptions been reviewed and updated as required? |  | Have assumptions been reviewed and updated as required and incorporated in the risk assessment?
Risks and assumptions around functional and non-functional requirements have been explored and captured
Have the relevant Lessons Learned been considered in the Concepts design?
|  | 0 |  | 0 |  |  | 0
1 |  | 0 | 4 | 0 | 2 |  | 0
Communication, Collaboration Stakeholders and Interfaces |  |  |  | 0 |  |  | 0
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Stakeholder Engagement Plan and Project Organisation Chart in place published in DMS. (If required - Maybe part of the PMP) |  |  | Stakeholder Engagement Plan has been updated including records of consultation and engagement |  | Stakeholder Engagement Plan is updated including records of consultation and engagement
Appropriate Collaboration events are planned (e.g. Design for Safety, Buildability, Design Reviews, co-ordination/interface reviews) |  |  |  |  | Concept evaluation workshops held and minuted with all stakeholders
Are interfaces with other projects understood and high level project interface milestones identified? |  |  | Have interfaces with other projects, operations or any others changed?
|  | 0 |  | 0 |  |  | 0
3 |  | 0 | 2 | 0 | 2 |  | 0
Procurement and Contract Administration - Delivery |  |  |  | 0 |  |  | 0
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Has the Procurement Strategy been agreed and documented? If it is outside the standard client procurement model was approval obtained. (If required, ) |  |  | Draft Contract Documentation prepared?. Have the Employers Requirements been included? |  | If required; has agreement to Procurement Plan been obtained?
If outside the standard client procurement model, has the support needed for the new contractors been discussed with the quality team and necessary actions taken? |  |  | Do the contracts deliver the expected levels of quality assurance?
|  | 0 |  | 0 |  |  | 0
2 |  | 0 | 2 | 0 | 1 |  | 0
Concepts Evaluation & Report |  |  |  | 0 |  |  | 0
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Has the Structure and approach for Concepts report been agreed between Client and design Contractors? |  |  | Have the "Concept Evaluation Criteria" been developed for each Concept that will be evaluated? |  | Has the Concept Report reviewed, agreed and signed off by Client/Owner Project Manager and does it fulfil the "Concept evaluation criteria"?
Has the basis for Concepts evaluation been agreed with the project team and key stakeholders?
Has an Concepts Report been produced with clear preferred Concept evaluated?
Leave this line - part of % complete calc. |  | 0.01 |  | 0.01 |  |  | 0.01
|  | 0.01 |  | 0.01 |  |  | 0.01
27 |  | 0 | 24 | 0 | 15 |  | 0
Plan and Mobilise Checkpoint (1) |  | 0.01 | Design Checkpoint (2) | 0.01 | Validate & Assure Checkpoint (3) |  | 0.01
Total as a percentage |  | 0.007407% | Total as a percentage | 0.008333% | Total as a percentage |  | 0.01333%

## Developed Design Assessment
Developed Design Stage - Quality Best Practice Self Assessment | [7 empty] | Plan and Mobilise Checkpoint (1) | 0.006897%
This self assessment is designed to evaluate the confidence and maturity of a project through a specific stage of the Client Project Process, aligned with the process method guidance. The assessment is to be conducted by, at a minimum, the Project Manager together with the PMO Representative and Quality Manager. | [7 empty] | Concepts Design Checkpoint (2) | 0.009091%
[8 empty] | Validate & Assure Checkpoint (3) | 0.01176%
Business Case | 0 |  |  | Project Manager |  | 0
Project | 0 |  |  | Quality Manager |  | 0
Checkpoint Timing Guidance - Checkpoint (1) - between 5-10% of the way through the stage. Checkpoint (2) 60-70% through the stage and checkpoint (3) about 90% of the way through the stage
Plan / Schedule / Cost
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Project Complexity assessment updated if required
Project Management Plan reviewed and updated, signed and published in DMS.
Detailed schedule for Developed Design in place, agreed with project team and Client/Owner. All contractor activities are integrated with external interfaces identified. |  |  | Developed Design schedule, drafted in the Concept stage, to be updated to reflect the output of the developed design phase. |  | Delivery Contractor Schedule(s) provided, based on client agreed project WBS and accompanied by a narrative articulating risks, assumptions etc. (assumes early procurement of Delivery Contractor)
A high level "end-to-end" project schedule in place aligned with the Client Project Process Guidance Understanding of the critical path. |  |  | High level "end-to-end" schedule updated to reflect the output of the developed design phase. Understanding of the critical path |  | High level "end-to end" schedule updated incorporating construction durations based on Delivery Contractor input. Understanding of the critical path
A plan to develop and gain approval for a the Developed Design project cost estimates is in place? The level of accuracy required has been established and agreed? |  |  | Developed design costs estimates ready for validation |  | Developed design costs estimates have been validation Validate / assure the cost, schedule & risk.
Revisit latest Lesson Learned from similar projects - reviewed and considered as required? |  |  | Lessons Learned review has been completed and LL incorporated into the developed design.
Brief for Delivery Contractor Integration Services up to next gateway in place |  |  | Next Gateway readiness assessment events planned |  | Developed Design Gateway readiness assessment events held and actions completed
Create Handover Plan and engage all stakeholders as required. |  |  | Have Engineering and Operations been fully engaged in line with the Handover Plan? (See Glossary) |  | Have Maintenance and Operations approved the Handover Plan?
|  | 0 |  | 0 |  |  | 0
8 |  | 0 | 6 | 0 | 5 |  | 0
Requirements and Design Management |  |  |  | 0 |  |  | 0
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Have prior Gateway actions been resolved or plan in place (if applicable)?
Has the Requirements Document been updated (with Developed Design level requirements and any changes to existing Client requirements and options requirements), approved by affected stakeholders ahead of design commencing, and published in DMS? |  |  | Change to requirements have been communicated formally via contract mechanisms Change has been incorporated in the Basis of Design as required |  | Have any last minute changes to requirements been communicated formally via contract mechanisms Last minute change to requirements has been incorporated in the Basis of Design as required. Have Benefits been quantified.
Is a Design Management Plan in place including definition of the plan for BIM and a Common Data Environment (CDE), a Design Review Schedule and a design change approval process |  |  | All design changes have been approved
The Design Brief is clear and unambiguous. Any assumptions that are needed have been specified. |  |  | Has appropriate buildability and constructability input/advice been sought? Have all relevant on-site surveys been carried out to inform the design?
All the design deliverables are clear |  |  | Developed Design Report reviewed by Client/Owner Project Manager and agreed. |  | All design deliverables met
Required technical specifications, models and drawings to the Client specified format are clear |  |  | All models and drawings are being prepared |  | All models and drawings have been delivered
Has the optimisation of the design been agreed versus the time and cost? I.e. a low cost, quick design may lead to a heavily over-engineered solution. Save now but pay later. |  |  |  |  | Have the design optimisation targets been validated?
Has the design schedule been updated with any delays incurred during the concept design?
Basis of design aligns with Requirements. |  |  | QVP has been discussed and agreed with the Delivery Contractor. Have safety critical assets been incorporated into the QVP?
All newly identified requirements loaded the into the QVP (Quality Verification Plan) |  |  | Updated QVP available |  | Updated QVP ready to be handed over to the production Design teams
|  | 0 |  | 0 |  |  | 0
10 |  | 0 | 7 | 0 | 5 |  | 0
Risks / Assumptions |  |  |  | 0 |  |  | 0
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Risk register updated since last Gateway and Risk management approach agreed. |  |  | Risk register with mitigation plans have been reviewed by the project team and externally assured or subject to a Fresh Eyes Review. |  | Risk register with mitigation plans has been reviewed & updated in line with the proposed solutions design.
Risks and assumptions around all types of requirements have been explored and captured (use of HAZOP and FMEA tools are planned where appropriate) |  |  | Have safety critical assets been identified and assessed in HAZOP and FMEA reviews.
Review and update project assumptions. |  |  | Assumptions appropriate for the phase have been updated, communicated to all relevant parties and incorporated into brief and scope documents. The risk of assumptions being false has been incorporated into the risk register. |  | All remaining project assumptions have been validated by the project team, added as risks in the risk register and referenced within cost, schedule, scope and works information. Client and Supplier assumptions have been reviewed jointly and any duplication removed and risk mitigation agreed
|  | 0 |  | 0 |  |  | 0
3 |  | 0 | 3 | 0 | 2 |  | 0
Communication, Collaboration Stakeholders and Interfaces |  |  |  | 0 |  |  | 0
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Stakeholder Engagement Plan and Project Organisation Chart updated and published in DMS. |  |  | Stakeholder Engagement Plan is updated including records of consultation and engagement. |  | Stakeholder Engagement Plan is updated including records of consultation and engagement and shared with the project team.
Stakeholder engagement activities planned and attendance at relevant forums agreed. |  |  |  |  | Developed Design evaluation workshops held with stakeholders and minuted.
Appropriate Collaboration events are planned (e.g. Design for Safety, Buildability, Design Reviews etc.) and Programme to Delivery transition activities agreed. |  |  | Have all buildability and constructability assessments been incorporated into the design?
High level DESIGN interfaces with other design disciplines, operations and other projects have been defined and agreed. Design Interface control points between disciplines have been documented |  |  | Have all design interfaces and control points been achieved and documented? i.e. between various design disciplines- civil, structural, architectural, MEP, systems, etc. |  | All project design interfaces are understood, defined, signed off and reflected in project schedule.
|  | 0 |  | 0 |  |  | 0
4 |  | 0 | 3 | 0 | 3 |  | 0
Procurement and Contract Administration - Delivery |  |  |  | 0 |  |  | 0
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
(If not carried out in the Concept stage) - Determine and agree the Procurement Strategy and document and obtain approval if it is outside of the standard client procurement model. |  |  | Populate the Draft Construction Contract Documentation. Ensure that the Employers Requirements are included. |  | Obtain approval of Construction Contract.
(If not carried out in the Concept stage) - If outside the standard client procurement model, has the support needed for the new contractors been discussed with the quality team and necessary actions taken? |  |  | Do the contracts deliver the expected levels of quality assurance?
Understand how the Works Information will be collated (Requirements documentation needs to be included in the WI). See Glossary. |  |  | Create project specific Works information published and configuration controlled in DMS.
|  | 0 |  | 0 |  |  | 0
3 |  | 0 | 3 | 0 | 1 |  | 0
Developed Design Report
Plan and Mobilise Checkpoint (1) |  | Score | Design Checkpoint (2) | Score | Validate & Assure Checkpoint (3) |  | Score | Comments
Has the Structure and approach for Developed Design report been agreed between Client and design Contractors? |  |  |  |  | Has the Developed Design Report been reviewed, agreed and signed off by Client/Owner Project Manager and does it fulfil the all the Project Requirements?
Leave this line - part of % complete calc. |  | 0.01 |  | 0.01 |  |  | 0.01
|  | 0.01 |  | 0.01 |  |  | 0.01
29 |  | 0 | 22 | 0 | 17 |  | 0
Plan and Mobilise Checkpoint (1) |  | 0.01 | Design Checkpoint (2) | 0.01 | Validate & Assure Checkpoint (3) |  | 0.01
Total as a percentage |  | 0.006897% | Total as a percentage | 0.009091% | Total as a percentage |  | 0.01176%